## Feuil1
NUTANIX CLUSTER NETWORK & POWER TEST PLAN
This test plan as been designed by Julien DUMUR, Senior Infrastructure Consultant at mikadolabs. to help others consultants to check cluster redundancy and compliance after a Foundation process.
A. PHYSICAL HARDWARE (REPEAT FOR EACH NODES)
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT / COMMENT | PASS / FAIL
1 | Configure the Hyperthreading CPU feature settings in the BIOS |  | Hyperthreading: Enabled
2 | Configure the XD CPU feature settings in the BIOS |  | XD: enabled
3 | Configure the Hardware Virtualization (HT) CPU feature settings in the BIOS |  | Hardware Virtualization (HT): Enabled
4 | Configure the VT Extensions CPU feature settings in the BIOS |  | VT Extensions: Enabled
5 | Configure the VT-D CPU feature settings in the BIOS |  | VT-D: Enabled
6 | Configure the Power Management: OS controlled settings in the BIOS |  | Power Management: OS controlled |  | PASS
7 | Confirm that the IPMI (out-of-band management) interface is accessible and that the remote console function works. |  | The out-of-band management interface can be accessed and the remote console function works. (ping and web access) |  | FAIL
B. NUTANIX BASIC CONFIGURATION
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT / COMMENT | PASS / FAIL
1 | Connect to the Prism UI and sign in |  | Successful sign in
2 | Confirm there are no Critical or Warning Alerts |  | No Critical or Warning alerts
3 | Confirm hardware summary shows the expected number of hosts / blocks |  | Hardware summary shows the expected number of hosts / blocks
4 | Go to "Settings > NTP Servers" and verify that the correct NTP servers are set | Configuring NTP Servers | NTP servers settings are correct
5 | Go to "Settings > Alerts Email Configuration" and verify that the correct email addresses are set in Email Recipients | Configuring Alert Emails | Alert email contacts are configured with prefered email addresses
6 | Go to "Settings > SMTP Server" and verify that the correct SMTP settings are set | Configuring SMTP Server | SMTP server setting is correct
7 | Test email configuration |  | Email are received
8 | Go to Settings > Email Alert Services and ensure that email services are on. |  | Email alert services are enabled
9 | If you're using SNMP, go to "Settings > SNMP Configuration", enable and configure SNMP | Configuring SNMP | SNMP enabled and configured
10 | If you’re using remote support services, go to Settings > Remote Support Services. Enable remote support so that you’re set up to receive timely Nutanix support. | Configuring Remote Support | A container named Reservation was created and configured per the recommended reservation values or, where greater availability is desired, with a capacity reservation greater than the recommended value.
B. NUTANIX DISTRIBUTED FILE SYSTEM
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT / COMMENT | PASS / FAIL
1 | Ensure that storage reservation is enabled instead in Prism. | Reserving Rebuild Capacity | Storage reservation is enabled
2 | Connect to the Nutanix cluster IP address via SSH and run the cluster status command. | cluster status | The command returns the status of all CVMs with a status of Up for all services.
3 | Verify that the correct number of containers have been created with the correct settings. | Storage Containers Summary | The correct number of containers with the correct settings exist.
4 | Verify that the container settings (replication factor, compression, deduplication) specified in the design or implementation document are applied. | Storage Containers Summary | The container settings specified in the design or implementation document are respected.
5 | Verify that the correct number of remote sites have been created with the correct settings. | Configuring a Remote Site | The correct number of remote sites with the appropriate settings exist.
6 | Verify that the correct number of protection domains have been created with the correct settings. |  | The correct number of protection domains with the appropriate settings exist.
7 | Verify that the correct number of consistency groups have been created with the correct settings. |  | The correct number of consistency groups with the appropriate settings exist.
8 | Verify that AOS licensing has been applied. | Licensing | AOS licenses are applied in the cluster.
9 | Make sure default passwords of user accounts on CVM, Prism Central and Hypervisor are changed. | KB 6153 | All default passwords should changed
C. MANAGEMENT SERVER
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT / COMMENT | PASS / FAIL
| Connect to management server: Prism Central |  | A successful connection to management is established.
| If you use SMTP notifications, confirm that SMTP settings have been configured | Configuring SMTP Server | SMTP server setting is correct
| Test email configuration |  | Email are received
| If you use service accounts, confirm that all management server services are configured to use the service account specified in the detailed design (excluding Prism Central). |  | All management services are configured to use the correct service account.
| On each node, confirm that each physical network interface of each network is connected to a different physical switch. | Network Visualizer | Each physical 1 GbE (if used) and 10 GbE network interface is connected to a different physical switch.
| If using Prism Pro or Ultimate, ensure appropriate licenses are applied in Prism Central. | Licensing | Prism Pro or Ultimate licenses are applied in Prism Central and enabled.
D. COMPUTE CLUSTERS
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT / COMMENT | PASS / FAIL
| Confirm that all hypervisor hosts are visible in the clusters. |  | All hosts are visible and active in the clusters.
| Confirm that all hypervisor hosts in the cluster are connected and in normal status. |  | All hosts in the cluster are connected and in normal status.
E. HYPERVISOR HOSTS
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT / COMMENT | PASS / FAIL
| Confirm that the networking host design follows Nutanix best practice guidelines | Nutanix AHV | Networking host design follows Nutanix best practices.
| On each node, confirm that the hostname and domain are configured | Change AHV Hostname | The hostname and domain are configured.
| On each node, Confirm that vNICX and vNICY (both 1 Gbps) are either set to Unused or not connected to a bond unless specified in the design | Open vSwitch Bridge | The vNICs are configured according to the appropriate best practice guide.
F. OPERATIONNAL VERIFICATION
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT / COMMENT | PASS / FAIL
1 | Deploy a VM using, assign the vNIC to each available port group one at a time and configure the network interface in the guest OS with an available IP address in that security segment.
2 | From the deployed VM, perform a ping to the default gateway of each network configured | ping gateway_ip | The gateway for each network segment responds to the ping with ≤1 ms latency.
3 | Evacuate all VMs from NODE1 except a test VM (nonproduction). |  | All VMs except test VMs are evacuated
4 | Start a continuous ping to the test VM | ping -t test_vm_ip | Test VM respond to ping
5 | Disconnect (logically or physically) all NODE1 vNICs used for management. |  | The VM is turned off and starts on another host.
6 | After you complete the task, reconnect the management connections. |  | Test VM respond to ping again
7 | Move back the test VM to the NODE1
8 | Simulate a host failure on NODE1 by connecting to the IPMI interface, then under the Power Control menu, select Reset Server, and click Perform Action. |  | After a short delay, the test VM should restart on a remaining host in the cluster and the Nutanix storage should remain connected and active for all other nodes.
9 | Repeat step 3 to 8 for each other NODE
G. POWER SUPPLY CHECKLIST
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT | PASS / FAIL
1 | Redundant power supply on first top of rack switch |  | Power supply is redundant
2 | Redundant power supply on second top of rack switch |  | Power supply is redundant
3 | Redundant power supply on OOBM switch |  | Power supply is redundant
4 | Redundant power supply on each node of the cluster |  | Power supply are redundant
H. POWER SUPPLY CHECKLIST
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT | PASS / FAIL
1 | Launch a continuous ping on NODE1 | ping -t host1_ip
2 | Unplug first power supply on NODE1 |  | NODE1 still respond to ping, no power outage
3 | Plug disconnected power supply and wait for the power supply to start
4 | Unplug second power supply on NODE1
5 | Plug disconnected power supply and wait for the power supply to start |  | NODE1 still respond to ping, no power ouotage
6 | Repeat steps 1 to 5 on each other node of the cluster
I. OOBM SWITCH POWER SUPPLY TEST
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT | PASS / FAIL
1 | Launch a continuous ping to OOBM switch | ping -t oobm_switch_ip | OOBM switch respond to ping
2 | On first OOBM switch, unplug the first power supply |  | OOBM switch connectivity is not lost
3 | Plug disconnected power supply and wait for the switch to start
4 | On first OOBM switch, unplug the second power supply |  | OOBM switch connectivity is not lost
5 | Plug disconnected power supply and wait for the switch to start
J. TOP OF RACK SWITCHES POWER SUPPLY TEST
| DESCRIPTION | COMMAND / KB | EXPECTED RESULT | PASS / FAIL
1 | Launch a continuous ping to first top of rack switch | ping -t top_of_rack1_ip | Top of rack respond to ping
2 | On first top of rack switch, unplug the first power supply |  | Top of rack connectivity is not lost
3 | Plug disconnected power supply and wait for the power supply to start
4 | On first top of rack switch, unplug the second power supply |  | Top of rack connectivity is not lost
5 | Plug disconnected power supply and wait for the power supply to start
6 | Launch a continuous ping to second top of rack switch | ping -t top_of_rack2_ip | Top of rack respond to ping
7 | On second top of rack switch, unplug the first power supply |  | Top of rack connectivity is not lost
8 | Plug disconnected power supply and wait for the power supply to start
9 | On second top of rack switch, unplug the second power supply |  | Top of rack connectivity is not lost
10 | Plug disconnected power supply and wait for the power supply to start
K. NODES NETWORK TEST
| DESCRIPTION | COMMAND / KB |  | PASS / FAIL
1 | Launch a continuous ping on NODE1 CVM | ping -t cvm1_ip | NODE1 CVM respond to ping
2 | Launch a continuous ping on NODE1 | ping -t host1_ip | NODE1 still respond to ping
3 | On first top of rack switch, unplug NODE1 Port1 and confirm that network connectivity is maintained without impact for all VLANs. |  | NODE1 and NODE1 CVM connectivity not lost
4 | Plug the disconnected cable and wait for the uplink
5 | On first top of rack switch, unplug NODE1 Port2 and confirm that network connectivity is maintained without impact for all VLANs. |  | NODE1 and NODE1 CVM connectivity not lost
6 | Plug the disconnected cable and wait for the uplink
7 | On first top of rack switch, unplug NODE1 Port3 and confirm that network connectivity is maintained without impact for all VLANs. |  | NODE1 and NODE1 CVM connectivity not lost
8 | Plug the disconnected cable and wait for the uplink
9 | On first top of rack switch, unplug NODE1 Port4 and confirm that network connectivity is maintained without impact for all VLANs. |  | NODE1 and NODE1 CVM connectivity not lost
10 | Plug the disconnected cable and wait for the uplink
11 | Put NODE1 into maintenance mode. Shut down the CVM. |  | All running VMs are evacuated and the host enters maintenance mode.
12 | Repeat steps 1 to 11 on each other node of the cluster
13 | Launch a continuous ping on each NODE and each CVM of the cluster
14 | Shutdown the first top of rack switch |  | Nodes and CVMs connectivity not lost
15 | Poweron the first top of rack switch and wait for it's restart
16 | Shutdown the second top of rack switch |  | Nodes and CVMs connectivity not lost
17 | Poweron the second top of rack switch and wait for it's restart